## Cost Time Analysis
Widget Analysis
Element | Points
Input Widgets
Sensorbox | 1
Add Button | 1
Remove Button | 1
Start Button | 1
Composite Widgets
Sensor-List | 1
Describing Widgets
Application Window | 1
WIDGET SUM | 6
x2 | 12 | Function Points (FP)
Lines of Code Analysis
C++ | 53
x12 | 636 | LOC
| 0.636 | KDL
COCOMO
Complex / Embedded Project | Hardware Sensors
Lock User inputs
Robust data packaging
Ei = 2.8 x (0.636)^1.2 | 1.633 | Persons Months
EAF
Cost Driver Factor
Required Reliability | High | 1.15 | Collected data must reach the backend
Product Complexity | High | 1.15 | Start /Stop, Add/Remove List
Main Storage Constraint | High | 1.06 | Real-time caching in mobiel RAM
Total EAF |  | 1.15 x 1.15 x 1.06
1.402
E = 1.402 x 1.633 PM | Developing Effort | E =2.29 | Person-Months
Calculate the length of a project in months based on the calculated person months
D = 2.5 · E c | D = 2.5 x(2.29)^{0.32} = 2.5 x1.303 = 3.26
3.26 Months
Staffing Demand
P = E/D | 2.29/3.26 | 0.7 Persons
Total Work Hours from COCOMO Effort
2.29x160 Hours | 366.4
Determine Personal Cost
366.4 x 100$ | 36640
Software Costs | 500
Hardware Costs | 1500
TOTAL SUM | 38640